## Slide 1: Overall Project Review Murcia, 24/07
Rafael Ataz
Jefe Departamento Iniciativas Europeas y Energías
24-25 July, 2019Kick off Meeting in Murcia
SCALE UP
INTERREG EUROPE
INFO-Regional Development Agency of Murcia Region

## Slide 2: What is recently achieved ?
Approval under conditions - 26/3/2019 (elegibility of expenditures)
Negociation of amended version April-may 2019
Preparation of G.A. & P.A. June
Signature of G.A. 24/6/2019 & signature of P.A. 9/7/2019
Kickoff meeting in Murcia 24-25/7/2019
Official start of the project 01/08/2019

## Slide 3: Index
1- OBJECTIVES
2- POLICY INSTRUMENTS
3- WORK PLAN & OUTPUTS

## Slide 4: SCALE UP OBJECTIVES
    MAIN OBJECTIVE:
    To contribute to European competitiveness and accelerate regional economic growth through the improvement of policy instruments linked to business growth and robustness, including specific measures and tools to support the capacity of SMEs to engage in growth in regional, national and international markets.
    SCALE UP will contribute, through the implementation of regional action plans, to the Programmes for Investing for Growth and Jobs and European Territorial Cooperation, increasing the competitiveness of industrial SMEs in the logistics, agrofood, bio-economy and ICT sectors in the participating regions.

## Slide 5: SUB-OBJECTIVES
    Exchange of experience and sharing of practices in the following thematic fields:
      New business collaborative models;
      Improvement of collaborative culture between science, technology, innovation and industrial companies’ system;
      Regional smart specialisation sectors in the form of partnerships/networks/cluster;
      Use and adaptation to new technologies and accessing to finance instruments
    Regional stakeholders’ involvement - Creation of 6 Stakeholders Action Groups (SAGs).
    Transfer of good practices and lessons learned to improve regional policy instruments.
    Design & development of 6 Action Plans for integrating and deploying best practices in business growth and scaling policies;

## Slide 6: POLICY INSTRUMENTS
Number | Name | Responsible Body Name
1 | ERDF Regional Operational Programme Murcia. Priority 3 (d) | General Directorate for Budget and European Funds, Regional Government of Murcia
2 | Opperational Programme EFRE 2014-2020 Hessen | Ministry of Economics, Energy, Transport and Regional Development, State of Hesse
3 | Regional Operational Programme Attica 2014-2020, TO 3, IP 3c | Region of Attica
4 | Regional Operative Programme ROP Lazio ERDF 2014 2020. | Lazio Region
5 | Regional Operational Programme of the Lubelskie Voivodeship 2014 - 2020 | Lubelskie Voivodeship
6 | D2N2 EU Structural and Investment Fund Strategy 2014-2020. Priority Axis 3 | Nottingham City Council

## Slide 7: Work Plan PHASE 1 “Interregional learning”
SEMESTER 1: 1/08/2019 – 31/01/2020
Desk Research on Business Scale up Policies
Benchmarking activities
Identification of Best Practices (BPs).
MAIN OUTPUS:
6 Stakeholders Action Groups (SAGs) created
1 management guideline developed;
1 Communication Strategy prepared;
SCALE UP Kick-off meeting organised
1 press kit; 7 Media appearance;
1 poster printed and displayed in public places in each SCALE UP region;
7 Launching Conferences organized;
1 website;
1 newsletter;
Minimum of 12 Best practices identified (2-3 BP per partner);
1 Digital Good practices Guide produced;
1st Interregional Policy Learning event organized in Poland + 2nd project meeting;
1 Auditor per region nominated (following national rules);
6 Regional Surveys produced;
1 Interregional Survey produced.

## Slide 8: Work Plan PHASE 1 “Interregional learning”
SEMESTER 2: 1/02/2020 – 31/07/2020
Organization of Interregional Site Visits (ISV).
MAIN OUTPUTS
4 Interregional site visits organized and partly implemented;
2nd Interregional Policy Learning Event on “New technologies as a tool to facilitate business scale up” organized in M9 in Italy + 3rd project meeting;
6 meetings with SAG members;
1 press conference; 7 Media appearance;
1 SCALE UP brochure designed, translated and printed;
2nd-newsletter;
1 Progress Report (PR1) submitted;
7 Presentations of SCALE UP project In local events.

## Slide 9: Work Plan PHASE 1 “Interregional learning”
SEMESTER 3: 1/08/2020 – 31/01/2021
Organization of Interregional Site Visits (ISV)
Peer Reviews between “importer” and “exporter” of each BP
MAIN OUTPUTS
2 Interregional Site visits implemented;
6 Peer Reviews implemented;
6 Reports (Roadmaps) developed;
1 internal meeting per partner institution;
3rd Interregional Policy Learning Event in Greece + 4th project meeting;
1 Press conference + 7 Media appearance;
3rd e-newsletter;
2nd Progress Report submitted;
6 SAG meetings organized.

## Slide 10: Work Plan PHASE 1 “Interregional learning”
SEMESTER 4: 1/02/2021 – 31/07/2021
Design of the 6 Regional Action Plans
MAIN OUTPUTS
1 Joint analysis of the Action Plans;
6 Actions Plans designed;
6 Actions Plans Local dissemination Events;
1 Risk Assessment Plan;
1 Press conference + 7 Media appearance;
4th SCALE UP e-newsletter;
5th Project meeting organized together with Co-creation Seminar and Final Conference in Brussels;
3rd Progress Report;
1 Stakeholder Action Groups meeting per region;
1 internal meeting per partner institution.

## Slide 11: Work Plan - PHASE 2
SEMESTER 5: 1/08/2021 – 31/01/2022
Implementation of the Action Plans
Updating of the project website
4th Progress Report from Phase 1
MAIN OUTPUTS
Website updates
1 progress report (covering last semester of phase 1)
SEMESTER 6: 01/02/2022 – 31/07/2022
Monitoring of the action plan implementation
Final dissemination event
MAIN OUTPUTS
1 project meeting (with participation of at least 90% of partners involved in phase 2)
Website updates
1 high-level political dissemination event (with min number of participants)
1 annual progress report

## Slide 12: Thank you! ¡Gracias! Danke! Merci! Grazie! Dziękuję! Σας ευχαριστώ!
Questions welcome